## Sheet1
Master's Thesis Plan: Quantiying the contributions of dispersal and niches to diversity maintenance in a microbial system
Week Beginning
Task | 27th April | 4th May | 11th May | 18th May | 25th May | 1st June | 8th June | 15th June | 22nd June | 29th June | 6th July | 13th July | 20th July | 27th July | 3rd Aug | 10th Aug | 17th Aug | 24th August | 31st Aug | 7th Sep | 14th Sep
Fit model to my data
Fit model to all data + log area/species
Create synthetic data to fit the model
Run simulation based verification of code
Seminar Diary 3
Seminar Diary 4
Meeting with James
Attempt to fit total of 50 data sets
Seminar Diary 5
Seminar Diary 6
Seminar Diary 7
Prep for presentation
Seminary Diary 8
Compare results across terrestrial/aquatic/taxonomic groups
Estimate critical area - difference between groups
Mean R^2 + adjusted, SD range, median values for parameters
Correlations between parameters using Spearman's rank
Seminary Diary 9
Write up results
Seminary Diary 10
Write up conclusion
Seminary Diary 11 + check/format
Lab Group Presentation (22nd June)
Send to supervisors for critique
Seminar Diary (1st July)
Apply improvements
HPC simulation using neutral theory
Write up HPC simulation
Send to supervisors for critique
Apply improvements
Final Project Submission (27th August)
Prep for viva
Vivas (14th September)